## CRM
Module | Sub-Module | Tasks | Estimates (Man Days) | Estimates (Man Days)
Onboarding | Party | API | 2
|  | UI | 2
| Agent | API | 1
|  | UI | 1
| Distributor | API | 1
|  | UI | 1
| Approvals | API | 0.5
|  | UI | 0.5
| Alerts | Worker
Authentication |  | API- Token Based, OAuth2 | 2
|  | UI | 0.5
Authorization | Claim Management | API | 2
|  | UI | 2
Communication | Integrations | Mailers | 4
|  | SMS | 2
|  | Whatsapp | 2
|  | UI | 2
Reports | Dashboard | API | 2
|  | UI | 4

## ECom
Module | Sub-Module | Tasks | Estimates (Man Days) | Estimates (Man Days)
Product Listing | Product Listing | API | 2
|  | UI | 2
Order | Add to Cart | UI – Cart | 1
|  | API – Cart | 2
| Payments | API – Payment Gateway Integration | 2
| Customer Selection/Addition | API – Customer Onboarding Integration | 1
|  | UI – Customer Onboarding Integration | 1
| Approvals, Payment Verification | Worker – Payment Update | 1
|  | API | 0.5
|  | UI | 1
|  | Worker – Alerts, Send Invoice | 1
Order Tracking |  | API | 0.5
|  | UI | 0.5
|  | Worker – Alerts | 1

## Technical
Email Integration
Whatsapp Integration
SMS Integration
Payment Integration